## Official Plan
HEAVENSTAY WELLNESS RESORT MANAGEMENT SYSTEM-HSWRMS (ISP392_IS2005_G1) — Project Task Plan
Weeks | # | Tasks | Interaction | PIC | Support | Complexity | Start-date | Act_Start-date | End-date | Duration (Days) | Status | Note
Week 1 | 1 | Project Initiating | Inter1 |  |  |  | 2026-09-07 | 2026-09-07 | 2026-09-10 | 4 | Done | Kickoff; confirm team roles & module ownership (5 modules / 5 members, full-stack DB→DAO→Controller→UI each)
| 1.1 | Project Planning + PM Plan | Inter1 | Tất Đạt | All | Medium | 2026-09-07 | 2026-09-09 | 2026-09-13 | 5 | Done
| 1.2 | Setup GitLab (6 module branches + shared core) | Inter1 | Tất Đạt | All | Simple | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2 | Done
| 1.3 | Meeting: Clarify + Business Rules | Inter1 | Gia Đạt | All | Medium | 2026-09-07 | 2026-09-08 | 2026-09-10 | 3 | Done
| 2 | Shared Foundation | Inter1 |  |  |  | 2026-09-07 | 2026-09-07 | 2026-09-13 | 6 | Done
| 2.1.1 | Documents | Inter1 | All | All | Medium | 2026-09-07 | 2026-09-07 | 2026-09-10 | 4 | Done
| 2.1.2 | Report 1: Project Introduction | Inter1 | All | All | Simple | 2026-09-07 | 2026-09-08 | 2026-09-10 | 3 | Done
| 2.2.1 | Draw Main Business Flow BF-01 – Guest Onboarding & Wellness Profile Setup | Inter1 | Đức Hoàng | Tất Đạt | Simple | 2026-09-07 | 2026-09-09 | 2026-09-13 | 5 | Done | Mỗi người tự nghiên cứu phần liên quan module mình
| 2.2.2 | Draw Main Business Flow BF-02 – Retreat Booking, Deposit & Check-In | Inter1 | Gia Đạt | Xuân Hòa | Simple | 2026-09-07 | 2026-09-09 | 2026-09-13 | 5 | Done | Mỗi người tự nghiên cứu phần liên quan module mình
| 2.2.3 | Draw Main Business Flow BF-03 – Spa/Therapy Scheduling & Session Fulfillment | Inter1 | Tất Đạt | Phương Thảo | Simple | 2026-09-07 | 2026-09-09 | 2026-09-13 | 5 | Done | Mỗi người tự nghiên cứu phần liên quan module mình
| 2.2.4 | Draw Main Business Flow BF-04 – Personalized Dining & F&B Service Fulfillment | Inter1 | Phương Thảo | Thành Vinh | Simple | 2026-09-07 | 2026-09-09 | 2026-09-13 | 5 | Done | Mỗi người tự nghiên cứu phần liên quan module mình
| 2.2.5 | Draw Main Business Flow BF-05 – Consolidated Checkout, Payment & Guest Feedback | Inter1 | Xuân Hòa | Gia Đạt | Simple | 2026-09-07 | 2026-09-09 | 2026-09-13 | 5 | Done | Mỗi người tự nghiên cứu phần liên quan module mình
| 2.2.6 | Draw Main Business Flow BF-06 – System Administration, Permission & Management Monitoring | Inter1 | Thành Vinh | Đức Hoàng | Simple | 2026-09-09 | 2026-09-09 | 2026-09-13 | 5 | Done
Week 2 | 3 | System Design_P1 | Inter1 |  |  |  | 2026-09-14 | 2026-09-14 | 2026-09-20 | 7 | Done
| 3.1 | Draw Context Diagram | Inter1 | All | All | Medium | 2026-09-14 | 2026-09-15 | 2026-09-18 | 4 | Done
| 3.2.1 | Draw Use Case Diagram - M1 (Authentication & Health Profile) | Inter1 | Đức Hoàng | Tất Đạt | Simple | 2026-09-14 | 2026-09-15 | 2026-09-18 | 4 | Done | Mỗi người tự vẽ UC module mình
| 3.2.2 | Draw Use Case Diagram - M2 (Retreat Booking & Accommodation) | Inter1 | Gia Đạt | Xuân Hòa | Simple | 2026-09-14 | 2026-09-15 | 2026-09-18 | 4 | Done | Mỗi người tự vẽ UC module mình
| 3.2.3 | Draw Use Case Diagram - M3 (Spa Scheduling (CORE)) | Inter1 | Tất Đạt | Phương Thảo | Simple | 2026-09-14 | 2026-09-15 | 2026-09-18 | 4 | Done | Mỗi người tự vẽ UC module mình
| 3.2.4 | Draw Use Case Diagram - M4 (F&B Nutrition (CORE)) | Inter1 | Phương Thảo | Thành Vinh | Simple | 2026-09-14 | 2026-09-15 | 2026-09-18 | 4 | Done | Mỗi người tự vẽ UC module mình
| 3.2.5 | Draw Use Case Diagram - M5 (Checkout & Analytics) | Inter1 | Xuân Hòa | Gia Đạt | Simple | 2026-09-14 | 2026-09-15 | 2026-09-18 | 4 | Done | Mỗi người tự vẽ UC module mình
| 3.2.6 | Draw Use Case Diagram - M6 (System Administration & Permission Management) | Inter1 | Thành Vinh | Đức Hoàng | Simple | 2026-09-14 | 2026-09-15 | 2026-09-18 | 4 | Done | Mỗi người tự vẽ UC module mình
Week 3 | 3 | System Design_P2 & SRS Completion | Inter2 |  |  |  | 2026-09-21 | 2026-09-21 | 2026-09-27 | 7 | Done | Order: Screen Flow → ERD → SRS finalization.
| 3.3.1 | Build Screen Flow Fragment - M1 Authentication & Health Profile (Screens 1-12) | Inter2 | Đức Hoàng | Tất Đạt | Simple | 2026-09-21 | 2026-09-21 | 2026-09-22 | 2 | Done | Map navigation only; Screen #1 is shared M1-M2. Use the common actor-access color legend and submit editable fragment.
| 3.4.2 | Build Screen Flow Fragment - M2 Retreat Booking & Accommodation (Screens 13-24) | Inter2 | Gia Đạt | Xuân Hòa | Simple | 2026-09-21 | 2026-09-21 | 2026-09-22 | 2 | Done | Connect package browsing → booking/deposit → my bookings → receptionist check-in/villa operations; align cross-links with M1/M5.
| 3.4.3 | Build Screen Flow Fragment - M3 Spa Scheduling (Screens 25-33) | Inter2 | Tất Đạt | Phương Thảo | Simple | 2026-09-21 | 2026-09-21 | 2026-09-22 | 2 | Done | Connect Customer spa flow, Receptionist extra booking, and Therapist dashboard/schedule/session detail using the shared legend.
| 3.4.4 | Build Screen Flow Fragment - M4 F&B (Screens 34-40) | Inter2 | Phương Thảo | Thành Vinh | Simple | 2026-09-21 | 2026-09-21 | 2026-09-22 | 2 | Done | Connect Chè/F&B flow.Customer xem Dietary Menu, chọn daily meal, order extra à-la-carte; Chef/F&B xem Meal Prep Dashboard/List, Meal Detail, allergy/dietary warning cần thiết và cập nhật Preparing/Ready
| 3.4.5 | Build Screen Flow Fragment - M5 Checkout & Analytics (Screens 41-48) | Inter2 | Xuân Hòa | Gia Đạt | Simple | 2026-09-21 | 2026-09-21 | 2026-09-22 | 2 | Done | Connect folio/invoice → final payment/result → checkout confirmation → review; add Manager analytics/report branches.
| 3.4.6 | Build Screen Flow Fragment - M6 Administration & Permission (Screens 49-56) | Inter2 | Thành Vinh | Đức Hoàng | Simple | 2026-09-21 | 2026-09-21 | 2026-09-22 | 2 | Done | Connect Admin and Manager dashboards to parameters, feature flags, permission matrix, delegation, audit log and system overview.
| 3.4.7 | Merge Master Project Screen Flow | Inter2 | All | All | Medium | 2026-09-22 | 2026-09-22 | 2026-09-24 | 3 | Done | After all fragments are submitted, merge into ONE project-wide Screen Flow (56 screens); normalize arrows, labels, colors and cross-module transitions.
| 3.5 | Design HSWRMS UI & Interactive Prototype based on Finalized Screen Flow | Inter2 | Tất Đạt | All | Medium | 2026-09-23 | 2026-09-23 | 2026-09-25 | 3 | Done | Figma UI Design + UI Kit/Design System + Clickable Prototype
| 3.5.1 | Draft Conceptual ERD Fragment - M1 Authentication & Health Profile | Inter2 | Đức Hoàng | Tất Đạt | Simple | 2026-09-23 | 2026-09-23 | 2026-09-24 | 2 | Done | Define M1 entities, key business attributes, PK/FK and relationships; reuse shared User/Role concepts instead of duplicating them.
| 3.5.2 | Draft Conceptual ERD Fragment - M2 Retreat Booking & Accommodation | Inter2 | Gia Đạt | Xuân Hòa | Simple | 2026-09-23 | 2026-09-23 | 2026-09-24 | 2 | Done | Model Retreat Package, Booking, Villa, check-in/residence-related data and shared Customer links; provide Crow-Foot cardinalities.
| 3.5.3 | Draft Conceptual ERD Fragment - M3 Spa Scheduling | Inter2 | Tất Đạt | Phương Thảo | Simple | 2026-09-23 | 2026-09-23 | 2026-09-24 | 2 | Done | Model Spa Service, Session, Therapist, Treatment Room and reservation relationships; support the therapist+room availability rule.
| 3.5.4 | Draft Conceptual ERD Fragment - M4 F&B Nutrition | Inter2 | Phương Thảo | Thành Vinh | Simple | 2026-09-23 | 2026-09-23 | 2026-09-24 | 2 | Done | Model meal/menu/order entities and the minimum dietary/allergy data relationships required by F&B operations.
| 3.5.5 | Draft ERD Fragment - M5 Checkout & Analytics | Inter2 | Xuân Hòa | Gia Đạt | Simple | 2026-09-23 | 2026-09-23 | 2026-09-24 | 2 | Done | Model Folio, charges, Invoice, Payment, Review;
| 3.5.6 | Draft Conceptual ERD Fragment - M6 Administration & Permission | Inter2 | Thành Vinh | Đức Hoàng | Simple | 2026-09-23 | 2026-09-23 | 2026-09-24 | 2 | Done | Model business parameters, feature flags, permissions/delegation and audit log; align User/Role references with M1.
| 3.5.7 | Merge Unified Project ERD | Inter2 | All | All | Medium | 2026-09-24 | 2026-09-24 | 2026-09-26 | 3 | Done | Merge all six fragments into ONE Crow-Foot ERD, remove duplicate entities and verify cross-module FK/cardinality.
| 3.6.1 | Complete SRS - M1 Functional Requirements + Entity Descriptions/Data Rules | Inter2 | Đức Hoàng | Tất Đạt | Simple | 2026-09-26 | 2026-09-26 | 2026-09-27 | 2 | Done | Write M1 screen/function specs and low-fi mockups; compile 3.2 Entity Descriptions + 3.3 Data Business Rules from all module inputs; clean Definitions/Acronyms.
| 3.6.2 | Complete SRS - M2 Functional Requirements + External API Inventory | Inter2 | Gia Đạt | Xuân Hòa | Simple | 2026-09-26 | 2026-09-26 | 2026-09-27 | 2 | Done | Write M2 screen/function specs and low-fi mockups; compile 5.2 External API Inventory using inputs from M1/M3/M5 (VNPay, Identity, Calendar/Email as applicable).
| 3.6.3 | Complete SRS - M3 Functional Requirements + Background Jobs + Final Document Integration | Inter2 | Tất Đạt | Phương Thảo | Simple | 2026-09-26 | 2026-09-26 | 2026-09-27 | 2 | Done | Write M3 screen/function specs and low-fi mockups; compile 5.3/Section 7 background jobs; merge Week 3 outputs and final-check TOC, Change Log, figures, Customer/HSWRMS terminology.
| 3.6.4 | Complete SRS - M4 Functional Requirements + Screen Inventory | Inter2 | Phương Thảo | Thành Vinh | Simple | 2026-09-26 | 2026-09-26 | 2026-09-27 | 2 | Done | Write M4 screen/function specs and low-fi mockups; insert the final Master Screen Flow and validate the complete 56-screen list in Section 5.1.
| 3.6.5 | Complete SRS - M5 Functional Requirements + Requirement Appendix | Inter2 | Xuân Hòa | Gia Đạt | Simple | 2026-09-26 | 2026-09-26 | 2026-09-27 | 2 | Done | Write M5 screen/function specs and low-fi mockups; compile III.1 Business Rules and III.2 System Messages from all modules, especially payment/checkout rules.
| 3.6.6 | Complete SRS - M6 Functional Requirements + Permission Matrix/Other Requirements | Inter2 | Thành Vinh | Đức Hoàng | Simple | 2026-09-26 | 2026-09-26 | 2026-09-27 | 2 | Done | Write M6 screen/function specs and low-fi mockups; complete 4.4 Permission Matrix and III.3 Other Requirements for RBAC, security, audit and limited Manager delegation.
Week 4 | 4 | Core Module Implementation | Inter2 |  |  |  | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late | Implementation: Begin deploying the core M1–M6 operations on the shared foundation.
| 4.1.1 | Register, verify email OTP, secure login | Inter2 | Đức Hoàng | Tất Đạt | Complex | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.1.2 | Build Register Form + Server-Side Validation | Inter2 | Đức Hoàng | Tất Đạt | Medium | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.1.3 | Generate & Send Email OTP (SendGrid) | Inter2 | Đức Hoàng | Tất Đạt | Medium | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.1.4 | Verify OTP & Activate Account | Inter2 | Đức Hoàng | Tất Đạt | Medium | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.1.5 | Login (Hash-Compare Password, Issue Session/Token) + Logout | Inter2 | Đức Hoàng | Tất Đạt | Complex | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.1.6 | Login/Register with Google/Facebook SSO | Inter2 | Đức Hoàng | Tất Đạt | Medium | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.2.1 | Browse Retreat Packages, filter by goal | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.2.2 | Browse Retreat Package List | Inter2 | Gia Đạt | Xuân Hòa | Simple | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.2.3 | Filter Packages by Goal (Weight Loss/Stress Relief/Yoga) | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.2.4 | View Package Detail Page | Inter2 | Gia Đạt | Xuân Hòa | Simple | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.3.1 | Request & Schedule Spa/Therapy Sessions (System-Driven Scheduling) | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.3.2 | Generate Scheduling Candidates (Time + Qualified Therapist + Compatible Room) | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.3.3 | Customer Enter Preferred Date/Time & Select Complete Candidate Bundle | Inter2 | Tất Đạt | Phương Thảo | Medium | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.4.1 | Pre-select Daily Meals (filtered by allergy/diet profile) | Inter2 | Phương Thảo | Thành Vinh | Complex | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.4.2 | Browse Menu Filtered by Allergy/Diet Profile | Inter2 | Phương Thảo | Thành Vinh | Medium | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.4.3 | Pre-Select Daily Meals | Inter2 | Phương Thảo | Thành Vinh | Medium | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.5.1 | Generate Customer Folio & Consolidated Invoice by Retreat Booking | Inter2 | Xuân Hòa | Gia Đạt | Complex | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.5.2 | Aggregate Package + Spa + F&B Charges by retreat_booking_id | Inter2 | Xuân Hòa | Gia Đạt | Complex | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.5.3 | Generate & Render Invoice Document | Inter2 | Xuân Hòa | Gia Đạt | Medium | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.6.1 | Configure Approved System Business Parameters | Inter2 | Thành Vinh | Đức Hoàng | Medium | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.6.2 | Build Business Parameter Management & Validation | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
| 4.6.3 | Configure Approved Operational Parameters | Inter2 | Thành Vinh | Đức Hoàng | Medium | 2026-09-28 | 2026-09-28 | 2026-10-04 | 7 | Late
Week 5 | 5 | Core Business Logic & Transactions | Inter2 |  |  |  | 2026-10-05 | 2026-10-06 | 2026-10-11 | 6 | Doing | Complete business rules, transactions, scheduling, payment, inventory..
| 5.1.1 | Dietary & Health Profile Form (explicit, unchecked consent) | Inter2 | Đức Hoàng | Tất Đạt | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.1.2 | Build Consent UI (Explicit, Unchecked Checkboxes - Decree 356/2025) | Inter2 | Đức Hoàng | Tất Đạt | Medium | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.1.3 | Create/Edit Dietary & Health Profile Form | Inter2 | Đức Hoàng | Tất Đạt | Medium | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.1.4 | Encrypt Sensitive Health & Dietary Data at Rest | Inter2 | Đức Hoàng | Tất Đạt | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.2.1 | Select Package/Dates/Villa + Initiate Deposit Payment | Inter2 | Gia Đạt | Xuân Hòa | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.2.2 | Select Package/Dates/Villa Type | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.2.3 | Calculate Deposit Amount | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.2.4 | Process VNPay Deposit Payment via Approved Payment Boundary | Inter2 | Gia Đạt | Xuân Hòa | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.2.5 | Handle VNPay Failure/Return/Callback Idempotency | Inter2 | Gia Đạt | Xuân Hòa | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.3.1 | System-Driven Scheduling Engine & Atomic Spa Reservation | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.3.2 | Filter Compatible & Available Treatment Rooms for Treatment Interval | Inter2 | Tất Đạt | Phương Thảo | Medium | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.3.3 | Filter Qualified & Available Therapists for Treatment Interval | Inter2 | Tất Đạt | Phương Thảo | Medium | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.3.4 | Revalidate + Lock Therapist/Room + Atomic Reservation | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.3.5 | Handle No Availability & HTTP 409 Concurrency Conflict | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.3.6 | Implement Customer Reschedule & System Recovery Flow | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.3.7 | Implement Attendance Confirmation & Reminder Timeline | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.4.1 | Daily Meal Prep Dashboard + Ingredient Demand & Inventory Alerts | Inter2 | Phương Thảo | Thành Vinh | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.4.2 | Aggregate Daily Meal Orders & Calculate Ingredient Demand | Inter2 | Phương Thảo | Thành Vinh | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.4.3 | Display Dietary Warnings + Ingredient Availability Alerts | Inter2 | Phương Thảo | Thành Vinh | Medium | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.5.1 | Process Final Payment, Update Villa Status | Inter2 | Xuân Hòa | Gia Đạt | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.5.2 | Check Pending/Unpaid Extra Spa & F&B Charges Before Checkout | Inter2 | Xuân Hòa | Gia Đạt | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.5.3 | Block Checkout if Outstanding Charges Exist | Inter2 | Xuân Hòa | Gia Đạt | Medium | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.5.4 | Process Final Payment | Inter2 | Xuân Hòa | Gia Đạt | Complex | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.5.5 | Update Booking & Physical Villa State after Checkout | Inter2 | Xuân Hòa | Gia Đạt | Medium | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.6.1 | Feature flag toggle per module | Inter2 | Thành Vinh | Đức Hoàng | Medium | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.6.2 | Build Feature-Flag Store | Inter2 | Thành Vinh | Đức Hoàng | Medium | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
| 5.6.3 | Toggle Feature Flag per Module (Admin UI) | Inter2 | Thành Vinh | Đức Hoàng | Simple | 2026-10-06 | 2026-10-06 | 2026-10-11 | 6 | Doing
Week 6 | 6 | Operational Workflows | Inter2 |  |  |  | 2026-10-12 |  | 2026-10-18 |  | To do | Actual workflows: Receptionist, Therapist, F&B, Checkout, Staff/Admin
| 6.1.1 | Manage Staff Accounts & Role Assignments | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-10-12 |  |  |  | To do
| 6.1.2 | Create Staff Account | Inter2 | Thành Vinh | Đức Hoàng | Medium | 2026-10-12 |  |  |  | To do
| 6.1.3 | Assign Approved Role (Receptionist/Therapist/F&B Staff/Manager/Admin) | Inter2 | Đức Hoàng | Tất Đạt | Complex | 2026-10-12 |  |  |  | To do
| 6.1.4 | Edit/Deactivate Staff Account | Inter2 | Thành Vinh | Đức Hoàng | Medium | 2026-10-12 |  |  |  | To do
| 6.2.1 | Dashboard of Arrivals + Check-In + Residence Declaration | Inter2 | Gia Đạt | Xuân Hòa | Complex | 2026-10-12 |  |  |  | To do
| 6.2.2 | View Daily Arrivals Dashboard | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-10-12 |  |  |  | To do
| 6.2.3 | Verify Customer Information | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-10-12 |  |  |  | To do
| 6.2.4 | Collect Required Customer Residence/ID Data at Check-In | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-10-12 |  |  |  | To do
| 6.2.5 | Encrypt Guest ID Data at Rest | Inter2 | Gia Đạt | Xuân Hòa | Complex | 2026-10-12 |  |  |  | To do
| 6.2.6 | Perform Check-In + Assign Physical Villa | Inter2 | Gia Đạt | Xuân Hòa | Complex | 2026-10-12 |  |  |  | To do
| 6.2.7 | Export Daily Residence Declaration Report | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-10-12 |  |  |  | To do
| 6.3.1 | View Therapist Daily Schedule & Treatment-Relevant Health Notes | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-10-12 |  |  |  | To do
| 6.3.2 | View Therapist Daily Schedule | Inter2 | Tất Đạt | Phương Thảo | Medium | 2026-10-12 |  |  |  | To do
| 6.3.3 | View Minimum Treatment-Relevant Health/Safety Projection | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-10-12 |  |  |  | To do
| 6.4.1 | Update Meal Order Lifecycle & Ingredient Inventory | Inter2 | Phương Thảo | Thành Vinh | Complex | 2026-10-12 |  |  |  | To do
| 6.4.2 | Reserve/Deduct Usable Ingredient Stock on PREPARING, then Update to READY | Inter2 | Phương Thảo | Thành Vinh | Complex | 2026-10-12 |  |  |  | To do
| 6.4.3 | Submit Review & Rating after Checkout | Inter2 | Xuân Hòa | Gia Đạt | Simple | 2026-10-12 |  |  |  | To do
| 6.5.1 | Submit Review & Rating Form | Inter2 | Xuân Hòa | Gia Đạt | Simple | 2026-10-12 |  |  |  | To do | Allow at most one review per eligible completed RetreatBooking.
| 6.6.1 | Configure detailed permission matrix per screen/role | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-10-12 |  |  |  | To do
| 6.6.2 | Design Permission Matrix Data Model | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-10-12 |  |  |  | To do
| 6.6.3 | Build Admin UI to Configure Matrix per Screen/Role | Inter2 | Thành Vinh | Đức Hoàng | Medium | 2026-10-12 |  |  |  | To do
| 6.6.4 | Enforce Receptionist No Unrestricted Access to Sensitive Health/Diet Data | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-10-12 |  |  |  | To do
Week 7 | 7 | Advanced Features & Module Completion | Inter2 |  |  |  | 2026-10-19 |  | 2026-10-25 |  | To do | Completed advanced features, privacy, audit, reports, reschedule, and self-test module.
| 7.1.1 | Manage System Master Data | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-10-19 |  |  |  | To do
| 7.1.2 | Manage Villa Categories (CRUD) | Inter2 | Thành Vinh | Đức Hoàng | Medium | 2026-10-19 |  |  |  | To do
| 7.1.3 | Manage Spa Treatments / Services Master Data | Inter2 | Đức Hoàng | Tất Đạt | Medium | 2026-10-19 |  |  |  | To do
| 7.1.4 | Manage Spa Treatments / Services Master Data | Inter2 | Đức Hoàng | Tất Đạt | Complex | 2026-10-19 |  |  |  | To do
| 7.2.1 | Manage Physical Villa Operational Status | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-10-19 |  |  |  | To do
| 7.2.2 | Update Physical Villa Status | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-10-19 |  |  |  | To do
| 7.2.3 | View Villa Status Board | Inter2 | Gia Đạt | Xuân Hòa | Simple | 2026-10-19 |  |  |  | To do
| 7.3.1 | Mark Session Completed / No-Show | Inter2 | Tất Đạt | Phương Thảo | Medium | 2026-10-19 |  |  |  | To do
| 7.3.2 | Mark Session Completed | Inter2 | Tất Đạt | Phương Thảo | Medium | 2026-10-19 |  |  |  | To do
| 7.3.3 | Mark Session No-Show | Inter2 | Tất Đạt | Phương Thảo | Medium | 2026-10-19 |  |  |  | To do
| 7.4.1 | Order Extra A-la-carte & Mark as Billable | Inter2 | Phương Thảo | Thành Vinh | Complex | 2026-10-19 |  |  |  | To do
| 7.4.2 | Order Extra A-La-Carte Item | Inter2 | Phương Thảo | Thành Vinh | Medium | 2026-10-19 |  |  |  | To do
| 7.4.3 | Expose Extra F&B Charge through M4→M5 Billing Boundary | Inter2 | Phương Thảo | Thành Vinh | Complex | 2026-10-19 |  |  |  | To do
| 7.5.1 | Revenue Dashboard (Pie/Bar by Package/Spa/F&B) | Inter2 | Xuân Hòa | Gia Đạt | Complex | 2026-10-19 |  |  |  | To do
| 7.5.2 | Build Revenue Aggregation Query (by Package/Spa/F&B) | Inter2 | Xuân Hòa | Gia Đạt | Complex | 2026-10-19 |  |  |  | To do
| 7.5.3 | Render Pie/Bar Revenue Dashboard | Inter2 | Xuân Hòa | Gia Đạt | Medium | 2026-10-19 |  |  |  | To do
| 7.6.1 | Delegate limited admin rights to Manager | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-10-19 |  |  |  | To do
| 7.6.2 | Delegate Limited Admin Rights to Manager | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-10-19 |  |  |  | To do
| 7.7.1 | Health Data Deletion Request & Deferred Processing | Inter2 | Đức Hoàng | Tất Đạt | Complex | 2026-10-19 |  |  |  | To do
| 7.7.2 | Customer Submit Health Data Deletion Request | Inter2 | Đức Hoàng | Tất Đạt | Medium | 2026-10-19 |  |  |  | To do
| 7.7.3 | Process Purge/Anonymization when Deletion Becomes Eligible | Inter2 | Đức Hoàng | Tất Đạt | Complex | 2026-10-19 |  |  |  | To do
| 7.7.4 | Log Deletion Action for Audit | Inter2 | Đức Hoàng | Tất Đạt | Medium | 2026-10-19 |  |  |  | To do
| 7.8.1 | View Booking Details & Itinerary Timeline | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-10-19 |  |  |  | To do
| 7.8.2 | View Booking Details | Inter2 | Gia Đạt | Xuân Hòa | Simple | 2026-10-19 |  |  |  | To do
| 7.8.3 | View Itinerary Timeline | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-10-19 |  |  |  | To do
| 7.9.1 | Manually Book Extra Spa Services (Billable) | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-10-19 |  |  |  | To do
| 7.9.2 | Receptionist Manual Spa Booking | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-10-19 |  |  |  | To do
| 7.9.3 | Expose Extra Spa Charge through M3→M5 Billing Boundary | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-10-19 |  |  |  | To do
| 7.10.1 | Minimize Sensitive Health Data Exposed to F&B Staff | Inter2 | Phương Thảo | Thành Vinh | Complex | 2026-10-19 |  |  |  | To do
| 7.10.2 | Build Data-Minimization View (Provide F&B Dietary/Allergy Projection Only) | Inter2 | Phương Thảo | Thành Vinh | Complex | 2026-10-19 |  |  |  | To do
| 7.10.3 | Enforce Data Minimization at Backend Authorization/DTO Layer | Inter2 | Phương Thảo | Thành Vinh | Complex | 2026-10-19 |  |  |  | To do
| 7.11.1 | Export Occupancy & Therapist Utilization Report (Excel) | Inter2 | Xuân Hòa | Gia Đạt | Medium | 2026-10-19 |  |  |  | To do
| 7.11.2 | Export Occupancy Report (Excel) | Inter2 | Xuân Hòa | Gia Đạt | Medium | 2026-10-19 |  |  |  | To do
| 7.11.3 | Export Therapist Utilization Report (Excel) | Inter2 | Xuân Hòa | Gia Đạt | Medium | 2026-10-19 |  |  |  | To do
| 7.12.1 | View sensitive-data access audit log | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-10-19 |  |  |  | To do
| 7.12.2 | Log Sensitive-Data Access Events | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-10-19 |  |  |  | To do
| 7.12.3 | View Sensitive-Data Access Audit Log | Inter2 | Thành Vinh | Đức Hoàng | Medium | 2026-10-19 |  |  |  | To do
| 7.12.4 | Admin Dashboard + Manager Dashboard + Role-Scoped System Overview | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-10-19 |  |  |  | To do
| 7.12.5 | Implement Role-Scoped Dashboards (S49 / S55 / S56) | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-10-19 |  |  |  | To do
| 7.13.1 | Unit Test & Self-Review (Authentication & Health Profile) | Inter2 | Đức Hoàng | Tất Đạt | Complex | 2026-10-19 |  |  |  | To do
| 7.13.2 | Unit Test & Self-Review (Retreat Booking & Accommodation) | Inter2 | Gia Đạt | Xuân Hòa | Medium | 2026-10-19 |  |  |  | To do
| 7.13.3 | Unit Test & Self-Review (Spa Scheduling (CORE)) | Inter2 | Tất Đạt | Phương Thảo | Complex | 2026-10-19 |  |  |  | To do
| 7.13.4 | Unit Test & Self-Review (F&B Nutrition (CORE)) | Inter2 | Phương Thảo | Thành Vinh | Complex | 2026-10-19 |  |  |  | To do
| 7.13.5 | Unit Test & Self-Review (Checkout & Analytics) | Inter2 | Xuân Hòa | Gia Đạt | Complex | 2026-10-19 |  |  |  | To do
| 7.13.6 | Unit Test & Self-Review (System Administration & Permission Management) | Inter2 | Thành Vinh | Đức Hoàng | Complex | 2026-10-19 |  |  |  | To do
Week 8 | 8 | Cross-Module Integration & Hardening | Inter3 |  |  |  | 2026-10-26 |  | 2026-11-01 |  | To do | Integrates M1–M6, DB/API contracts, RBAC, billing boundaries, third-party APIs and hardening
| 8.1 | Reconcile Development Schema & Module Migrations with Approved SQL Server Baseline | Inter3 | Tất Đạt | Thành Vinh | Complex | 2026-10-26 |  |  |  | To do
| 8.2 | Integrate M2/M3/M4 Billing Boundaries with M5 | Inter3 | Xuân Hòa | Gia Đạt | Complex | 2026-10-28 |  |  |  | To do
| 8.3 | Integrate Identity Roles (M1) with M6 RBAC/Permission Enforcement | Inter3 | Thành Vinh | Đức Hoàng | Complex | 2026-10-28 |  |  |  | To do
| 8.4 | Integrate Third-Party APIs: SSO (M1), VNPay (M2/M5), Email Notification (M3) | Inter3 | Gia Đạt | Tất Đạt | Complex | 2026-10-30 |  |  |  | To do
| 8.4 | End-to-End Cross-Module Integration & Contract Testing | Inter3 | All | Tất Đạt | Complex | 2026-10-31 |  |  |  | To do | Validate M1→M6 dependencies, REST contracts, security, migrations, booking→spa/F&B→folio→checkout flows before Week 9.
Week 9 | 9 | System Testing & Documentation | Inter3 |  |  |  | 2026-11-02 |  | 2026-11-08 |  | To do | Perform full system testing after integration, fix UI/backend/security/concurrency bugs, review SRS/SDS, and finalize the User Manual based on actual implementation.
| 9.1 | Fix UI Bugs | Inter3 | All | All | Medium | 2026-11-02 |  |  |  | To do
| 9.2 | Fix Backend / Integration / Security / Concurrency Bugs | Inter3 | All | Thành Vinh | Complex | 2026-11-02 |  |  |  | To do
| 9.3 | Merge SRS/SDS: each member submits their own module's section | Inter3 | All | Tất Đạt | Complex | 2026-11-04 |  |  |  | To do | Gia Đạt + Thảo + Tất Đạt tổng hợp thành bản thống nhất.Each member updates the as-built section of their module.Do not overwrite approved requirements with implementation assumptions.
| 9.4 | Prepare User Manual (each member writes their own module's section) | Inter3 | All | Phương Thảo | Medium | 2026-11-05 |  |  |  | To do | Hoàng tổng hợp
Week 10 | 10 | Final Presentation & Closing | Inter3 |  |  |  | 2026-11-09 |  | 2026-11-15 |  | To do | Prepare slides, rehearse, demo the integrated system, perform a final check of the source code/documents, and submit the project.
| 10.1 | Prepare Slides (each member presents their own module) | Inter3 | All | All | Simple | 2026-11-09 |  |  |  | To do
| 10.2 | Rehearse Presentation | Inter3 | All | Thành Vinh | Medium | 2026-11-11 |  |  |  | To do
| 10.3 | Demo System (all 6 modules + integration) | Inter3 | All | Tất Đạt | Complex | 2026-11-12 |  |  |  | To do
| 10.4 | Submit Source Code & Documents | Inter3 | All | Xuân Hòa | Medium | 2026-11-13 |  |  |  | To do
| 10.5 | Final Project Review | Inter3 | All | Thành Vinh | Medium | 2026-11-14 |  |  |  | To do
NOTE | Thực tế 11/11 là buổi học cuối của môn trước khi lên hội đồng

## Đánh giá thành viên
Bảng đánh giá thành viên
STT | Tên thành viên | MSV | Điểm
1 | Tăng Xuân Hòa | HE180798
2 | Nguyễn Gia Đạt | HE181035
3 | Nguyễn Tất Đạt | HE181883
4 | Phạm Thành Vinh | HE186593
5 | Vũ Phương Thảo | HE204054
6 | Lê Đức Hoàng | HE204568